## Sheet1
Listing | Musts | Wants | Assumptions | Constraints | Objectives | Milestones | Specifications | Deliverables | Problem Statement | Risks | Remedies | Responsibilites
1 | Able to move around the campus autonomously | Carry heavy weight (100kg+) | It is allowed to use the campus roads & facilities | The wheels can last while operating on university roads | Automate deliveries in KAU |  | detect objects within 5m | A delivery robot | To reduce the need for manual transport of food, equipment and documents . A robotic autonomous device should be developed This way, workers/students can stay at their respective stations/classes rather than having to walk back and forth across the campus. | weak wide fidelity signal | use 4g | Object detection
2 | includes a storage unit for the shipments. | Operate at road speed | There is no network interference | Availability of the parts required. | Reduce the time wasted by delivering manually |  | avoid time of 10ms | a simple user interface |  | A part breaks down | Replace with higher quality part. | Mechanical building of the robot
3 | Avoid obstacles | battery life lasts atleast one complete trip. | Drivers obey the road laws. | Should not harm humans. | Make use of the available space |  | weight of the robot less than xxkg | a lockbox to store the food,documents…. |  | lockdown again | work from home | navigation
4
5 |  |  |  |  | Increase the knowledge of robotics |  | • Size of package at least x m3
6 |  |  |  |  | Help reduce physical work
7 |  |  |  |  | Encourage other students to work & produce working solutions
8 | All electronics are insulated from users | eco-friendly with no gas emission | · No components are DOA (dead on arrival) | · Must be done before the end of the spring semester
9 | deliver the packages safely | • The packages are safely secured such that they cannot be stolen | the university network covers the whole campus or at least a 4G connection is available | · Environmentally friendly material
10
11
12
13
14